## Daily Status
2022-09-02
Module Name | Automation PBI No. | PBI Status | Total Test cases No. | Completed Test Cases No. | Pending Test Cases No. | Reason for Pending Test Case | Out of Scop Test Cases No. | PBI No. | Module Name | No. of Test Cases
Annual Business Meeting | 55946 | InProgress | 30 | 20 | 10 | Pending to Create | 0
[8 empty] | Manual Bug OR PBI No. | Manual Bug OR PBI Status | Assign To Developer Name
District Success Plan | 54933 |  | 4 | 3 | 1 |  | Unable to click on "Add A Goal" button | 55129 | Closed
District Finance Portal | 54808 |  | 4 | 3 | 1 |  | Technical challenge for web table handling | 55127 | In-progress | Perm
Club Financial | 53270 |  | 4 | 2 | 2 |  | Technical challenge for file upload | 55213 | In-progress | Jinrikisha
No. | Master Module | Module Name | Completed | Note
1 | Club Central | Add MemberShip | YES
2 |  | Submit Education Awards | YES
3 |  | Submit Payment | YES
4 |  | Club Roster | YES
5 |  | Club Contact and Meeting information | YES
6 |  | Club Officer Assignment | YES
7 |  | Club Success Plan | YES
8 |  | Club Demographics | YES
9 |  | ASCO | YES
10 |  | Club Events | YES
11 |  | Club Achivements | YES
12 |  | Administrative Reports | YES
13 |  | Eligibility Assistant | YES
14 |  | Distinguished Performance Reoprt | No
15 |  | Club Financials | No | Technical Issue found
16 | District Central | Area Director Club Visit Report | YES
17 |  | District Success Plan
18 |  | Division and Area Director Training | YES
19 |  | Leads and Propective Clubs | YES
20 |  | Club Officer Training Reports | YES
21 |  | District Awards | No
22 |  | District Finance Portal | No
23 |  | Distinguished Performance Reoprt | No
24 |  | Reports
25 |  | District Leards Tools | No
26 |  | Pathways Adoptions Rates | No
27 |  | Wire Transfer Instruction | YES
28
29 | ATO |  | YES
30 | Shop |  | YES
31 | Pathway Purchase |  | YES
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56

## Manual and Automation
No. | Modul Name | Total Manual Test cases Number | Total Automation Test Script Number | Manual Test Case Convert to Automation Test Case Script | Pending test cases for create script | Resone for pending test cases script
1 | Add Membership | 35 | 13 | 27 | 0 | Some test cases out of scop and one is CRM side
2 | Submit Payment | 31 | 5 | 22 | 0 | Some test cases out of scop
3 | Submit Education Award | 46 |  | 34 |  | Some test cases out of scop
4 | Club Roster | 43 |  | 29
5 | Club Officer Assignment | 34 |  | 22
6 | Club Event | 18 |  | 17
7 | Club Contact & Meeting Info | 25 |  | 23
8 | Club Achievements | 12 |  | 7
9 | Club Demographics | 24 |  | 14
10 | Eligibility Assistant | 24 |  | 20
No. | Module Name | Total No of Automation Test Case Script | Automation Test Case Name | Manual Test Cases Name
1 | Add Membership |  | TC001_NoDual InvalidName ValidMemberID | Verify Add Membership option display on screen
Verify Add Membership header display after click on Add Membership option
Verify Club Id and Club Name display, after click on Add Membership option
Verify No, Dual/Reinstated Member radio option by default selected, after click on Add Membership option
Verify Search button disabled if user not entered anything in mandatory field
Verify Search Member using wrong Last Name and valid Email Id
|  |  | TC002_NoDual InvalidName ValidEmailID | Verify Search Member using wrong Last Name and valid Member Id
|  |  | TC003_NoDual ValidLName InVMemberID | Verify Search Member using Last Name and wrong Member id
Verify Cancel button functionality in Popup window
|  |  | TC004_NoDualValidLName InVEmailID | Verify Search Member using Last Name and wrong Email id
|  |  | TC005_NoDualValidLName VEmailID | Verify Search member using the valid Last Name and Email Id
|  |  | TC006_NoDualValidLName VMemberid | Verify Search member using the valid Last Name and Member Id
|  |  | TC007_PositiveMemberIDNoDualReinstated | Verify Confirm button functionality in Popup window
|  |  | TC008_PositiveMemberIEmailDNoDualReinstated Membership | Verify display country dropdown
|  |  | TC013_VerifyDeceasedMember | Verify user get message like member not found if user enter Deceased member data
|  |  | TC014_VerifyTerminatedMember | Verify user get message like member not found if user enter Terminated member data
|  |  | TC015_VerifySuspendedMember | Verify user get message like member not found if user enter Suspended member data
|  |  | TC016_VerifyMemberAlreadyIntoSubmitPayment | Verify open submit payment link pop up box when user search member into No, Dual/ Reinstated Member if user search member who is already into submit payment page